CODE TROOPERS

Official Club Policy Document

# ARTICLE 21: ACTIVITY PLANNING & EXECUTION FRAMEWORK

## Purpose

This framework defines the standard procedure for planning, approving, conducting, documenting, and closing all Code Troopers activities which are conducting offline using college resources including:

- Workshops

- Skill Development Camps

- Bootcamps

- Guest Lectures

- Hackathons

- Competitions

- Technical Talks

- Project Exhibitions

- Community Events

No activity shall be conducted without following this framework.

#### NOTES : If the event is conducted online and any stage of this event does not include any college resource then we need not follow the approval process but the faculty co-ordinator should be informed about it.

# 21.1 Workshop Execution Procedure

## Phase 1: Planning

Before proposing a workshop, the organizing team shall conduct an internal planning meeting.

The team must finalize:

- Workshop topic

- Faculty coordinator

- Duration

- Target audience

- Expected participants

- Resource requirements

- Venue preference

## Phase 2: Syllabus Preparation

If the workshop involves teaching a technology or skill, a detailed syllabus must be prepared.

For multi-day workshops, a day-wise breakdown shall be documented.

Example Format

| Day | Topics Covered | Activities | Deliverables |
| --- | --- | --- | --- |
| Day 1 | Introduction & Basics | Hands-on Setup | Environment Setup |
| Day 2 | Intermediate Concepts | Practical Implementation | Mini Project |
| Day 3 | Advanced Topics | Project Development | Final Project |

The syllabus document must be reviewed by the Learning & Platform Development Team before approval.

## Phase 3: Venue Verification

Before finalizing the event, the organizing team shall verify:

- Venue availability

- Seating capacity

- Projector availability

- Internet availability

- Power backup

Venue verification shall be done with assistance from:

- Department HOD

- Mr. Deepak Rao

- Faculty Coordinators

The venue selected must comfortably accommodate the expected number of participants.

## Phase 4: Event Documentation Preparation

An Event Proposal Document shall be prepared containing:

Mandatory Information

- Event Name

- Event Date

- Organizing Team

- Faculty Coordinator

- Venue

- Expected Participants

- Event Description

- Workshop Brief

- Objectives

- Expected Outcomes

- Detailed Schedule

- Resource Requirements

## Phase 5: Activity Request Approval

After preparing the Event Proposal, an Activity Request Form must be prepared.

Important Rule

The Activity Request Form shall be submitted to the HOD only through a faculty member.

The organizing team may provide the details of the event, but official submission must be done by:

- Faculty Coordinator

- OR Any supporting faculty member (Mr.Deepak Rao/ Ms.Prithi / Mr.Ragvendra G.S)

## Phase 6: HOD Approval

Before proceeding with any preparations, the organizing team shall obtain verbal approval from the HOD.

Only after approval may:

- Posters be created

- Registrations begin

- Announcements be released

- Resources be booked

## Phase 7: Poster Approval

For Internal Club Activities

All promotional posters shall be approved by the E.O officer of college before circulation.

No poster shall be publicly circulated without approval.

Poster Checklist

- Correct Date

- Correct Venue

- Correct Time

- College frame and logo should be proper.

- Club logo should be used.

- Faculty Approval

- Registration Link/ QR

#### NOTE: Reach Out to the club media team for poster making

## Phase 8: Registration Management

A Google Form shall be created. The registration form must include:

- Name

- USN

- Branch

- Semester

- Contact Number

- Email

Participant Limit Control

The form must use a google response-limiting extension to automatically stop accepting responses once the approved participant limit is reached.

## Phase 9: Attendance Management

The organizing team shall prepare an official attendance sheet. Attendance sheets must contain:

- College Logo

- Event Name

- Date

- Participant Name

- USN

- Signature (should be signed by the participants during the event on hardcopy)

## Phase 10: Attendance Submission

At the end of each day:

Hard Copy

Attendance sheet shall be submitted to the Faculty Coordinator.

Soft Copy

Scanned attendance sheets shall be shared with all faculty members of the respective year to ensure attendance benefits are provided to participants.

## Phase 11: Event Documentation

Every event must be documented in the official Code Troopers Google Drive. The following Folder structure shall be maintained:

{Event Name} /

- Detail Event Document

- Posters

- Registration Forms

- Scanned Attendance sheets

- PPTs

- Resources

- Photos

- Videos

- Certificates

- Feedback Forms

## Phase 12: Certificate Generation

Certificates shall be generated using the official Code Troopers E-Certificate Generator.

Certificate records shall be stored in the event folder.

## Phase 13: Post Event Activities

Within 48 hours of completion, the organizing team shall :

- Upload all documents

- Submit event report

- Upload attendance records

- Publish event photographs

- Share feedback analysis

These will be verified by the Event and Operation team.

All organizers are encouraged to publish a professional LinkedIn post summarizing the event.

# 21.2 Hackathon Execution Procedure

Due to the scale and budget involved, Hackathons require an enhanced approval process.

## Phase 1: Concept Development

The organizing committee shall define:

- Hackathon type - intra / inter

- Hackathon Themes

- Duration

- Participation Model - Stages / Rounds

- Expected Team Size

- Expected Registrations

## Phase 2: Proposal Preparation

A Comprehensive Hackathon Proposal Document shall be prepared. The proposal shall contain:

### Event Overview

- Event Name

- Dates

- Venue

- Theme

- Description

- Over all budget

### Organizational Structure

- Organizing Committee

- Student Coordinators

- Faculty Coordinators

### Participation Details

- Expected Participants

- Expected Colleges

- Registration Structure

### Budget Planning

Detailed Expense Breakdown

- Food & Accommodation

- Prize pool

- Goodies & Merch ( if any )

- Decoration ( if any)

- Miscellaneous Expenses

### Sponsorship Planning

Sponsor Categories ( optional )

- Title Sponsor

- Gold Sponsor

- Silver Sponsor

- Community Partners

Expected sponsorship amounts shall be documented.

### Event Flow

Example

- Round 1 → Idea Submission

- Round 2 → Screening

- Round 3 → Prototype Development

- Round 4 → Final Presentation

- Round 5 → Winner Declaration

### Objectives

Clearly define:

- Learning outcomes

- Innovation goals

- Industry exposure

- Networking opportunities Etc

### Expected Outcomes

- Number of Projects

- Industry Collaborations

- Student Engagement

- Startup Opportunities

## Phase 3: Dean Research Approval

The proposal shall be submitted to: Dean Research.

No promotions, sponsorship activities, registrations, or announcements shall begin until approval is received.

## Phase 4: Promotion & Sponsorship

After approval, the following may begin:

- Sponsorship Outreach

- Poster Release ( Confirm with Dean Research, generally hackathons dont need E.O approvals)

- Social Media Campaign

- College Outreach

- Website Release

- Registration Launch

## Phase 5: Event Execution

The Hackathon Organizing Committee shall maintain throughout the event:

- Registration Records

- Attendance Records

- Mentor Allocation

- Judging Rubrics

- Financial Records

- Availablity of hospitality and Resources

## Phase 6: Closure Report

Within seven days of completion, a Hackathon Closure Report shall be prepared containing:

- Participant Statistics

- Financial Summary

- Sponsor Summary

- Winner Details

- Event Photos

- Media Coverage

- Feedback Analysis

- Recommendations

The report shall be archived in the official Code Troopers Drive.

Also submitted to the respective faculties involved ( Dean Research etc)

Golden Principle

“If an activity is not documented, it is considered not conducted.”

Every event, workshop, hackathon, competition, or initiative must leave behind complete documentation for future teams.